## How to use the Template
Who is this template for? This template is useful for individuals who need to develop an operational plan for their organisation, and who wish to align their operational plan clearly with their organisational strategic plan. When should I use it? Operational plans should be developed based on a current organisational strategic plan including strategic aims and strategic actions. When develop an operational plan? Plan a year ahead at a time, and keep it simple. Adapt this template as needed. 1. Activities – recommend brainstorming activities required to deliver each strategic action with relevant project staff 2. Timeframe – when do activities need to start and be completed? 3. Resources needed – people, materials, equipment, services, transport, training / staff development. Can summarise costs based on previous experience. If no previous experience, a basic costing exercise may be needed. 4. Allocate person responsible 5. Check - check for dependencies (i.e. if the success of one activity depends on another activity being completed first) and ensure that the scheduling works. Also check that nothing has been missed and against existing project commitments to ensure everything has been captured in terms of both activities to deliver and when these need to be delivered by. What next? Once your operational plan is in place, you can use this as a basis to: • Develop individual staff workplans • Develop a full budget - for budgeting generally, you might find this site helpful: http://www.mango.org.uk/Guide/Budgeting • Develop a finance strategy

## Operational Plan Template
Strategic objective | Strategic Action | Activities (Inputs) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Person leading (supporting) | Resources required
What is change you want to see in this issue in three years’ time? | The strategies used to achieve the strategic objective | What you will actually do (resources put in)
Objective 1 | 1.1 | Task 1 | bar: Jan
| 1.1 | Task 2 | bar: Feb to Apr
| 1.1. | Task 3 | bar: Mar to May; Oct to Dec
| 1.2 | Task 1 | bar: Apr to Jul
| 1.2 | Task 2 | bar: Aug to Dec
| Etc | Etc
Objective 2
Objective 3
Etc