## Monitoring Matrix
Monitoring Workflow | Rationale | Indicators | Baseline | Targets | Measure | Methodology | Frequency | Tools | Responsibility
Impact | The 130,000ha of WSP Forest are managed sustainably, supporting biodiversity and the livelihoods of 6,630 people, acting as a model for sustainable forest management in Cambodia
Outcome | By March 2019, the strengthening of relationships between key WSPWS stakeholders (Government and local communities), enables the Sanctuary to harbour a stable population of five critically endangered bird species and increases human wellbeing in four surrounding villages. | 0.1 Increased food security in four target villages (5,052 people), with a reduction in the percentage of households with sufficient food for less than five months of the year from 38% of households to 25% By end of Yr.3. | 38% of households have sufficient food for less than five months of the year | 25% of households have sufficient food for less than five months of the year | 0.1 Participatory Rural Appraisal undertaken 2018 compared with 2014 (pre) and 2016 (start of project) baselines. | 1. Conduct baselines 2. PRA 2018 | Annual | 1. Baselines 2. PRA | Livelihoods Programme Manager
|  | 0.2 Beneficiaries from 7 target villages are empowered to raise their voice through local institutional strengthening, and voice their requests in meetings and the zoning plan. | Beneficiaries have limited venues to raise their voice | Beneficiaries ideas and concerns are included in the zoning plan and they feel heard through participating in quarterly meetings | 0.2 Meetings minutes, zoning plan process report | 1. Conduct quarterly meetings 2. Include beneficiaries ides in the zoning plan | Annual | 1. Quarterly meeting minutes 2. Zoning plan | Community Outreach Officer
|  | 0.3 Stable populations of five Critically Endangered species within WSPWS by end of Y3. | Vulture restaurant (2016 highest in September): 110 White-shoulder Ibis (2016 highest in August): 272 Giant Ibis: 9 nests successfully fledged 16 chicks so 18 adults plus 16 chick=34 | Stable population compared with 2016 baseline | 0.3 BirdLife biodiversity team led species census results compared with 2016 baseline. | Each species census will be conducted according to the season for roofting, nesting and the vulture restaurant | Annual | 1. Species census 2016 baseline 2. Species census 2018 | Biodiversity Senior Project Officer
Output 1 | Local consultation structures established at village and district level, equitably representing the views of constituents | 1.a Seven Village Forums established with equal representation of women and men (50% women, 50% men). | 0 Village Forums | 7 Village Forums, equal gender representation | 1.a.1 Meetings are held regularly and attendance list shows equitable participation of women and men, evidenced by equal sex ratio of women : men attending meetings 1.a.2 Dialogue in village meetings show enhanced understanding of management planning process over the three year project implementation period, evidenced by meeting minutes and participatory learning assessment survey at end of Yr.3 | 1. Quarterly consultation meetings with Village Forums 2. Endorsement at Commune level 3. Protocol for beneficiaries counting into database | Six-monthly | 1. Beneficiaries database 2. Attendance lists 3. Meeting minutes 4. Village Forums establishment certificates 5. Gender representation strategy 6. Participatory Learning Assessment Survey
|  | 1.b WSPWS Stakeholder Forum established and working effectively. | 0 Stakeholders Forum | 1 Stakeholders Forum, regular consultations, requests included in the zoning plan | 1.b.1 List of attendees at stakeholder meetings includes representatives from all relevant interest groups including representatives from village forums. 1.b.2 Requests from village forum representatives on traditional-use are collected and presented to Provincial level authorities. These requests and the rice field maps are included in the WSPWS zonation process, evidenced by forum minutes and zoning plan. | 1. Quarterly meetings with Stakeholders Forum 2. Collection of Village Forums representatives requests | Six-monthly | 1. Beneficiaries database 2. Attendance lists 3. Meeting minutes 4. Report on Village Forums representatives requests for the zoning plan
|  | 1.c By March 2019, local community views on traditional use are included in WSPWS zonation process and plan alongside rice field maps | Local community views are not taken into account | Local community views on traditional use are included in WSPWS zonation process and plan alongside rice field maps | 1.c.1 Forum minutes, zoning plan | 1. Local community views are collected during quarterly and zoning meetings 2. Rice field maps are used to show the land used by local communities | Annual | 1. Quarterly meeting minutes 2. Zoning meetings minutes 3. Rice field maps
Output 2 | Community land-use plans (maps of land holdings and rice fields) and conservation agreements finalised within at least four villages neighbouring Western Siem Pang WS | 2.a By the end of year two, three village land-use maps are complete. | 0 Villages with land-use maps | 3 Villages have land-use maps | 2.a Village land-use maps endorsed by Commune Chiefs. | 1. Shape files of land-use maps for 3 villages 2. Endorsement at Commune level | Annual | 1. Progress reports from the Department of Land Management, Urban Planning and Construction 2. Shape files 3. Land-use maps signed and stamped by Commune Chief | Livelihoods Project Officer
|  | 2.b By the end of year three, the remaining village land-use maps are complete (total of four complete) resulting in 450 households in four target villages with maps of land holdings and rice fields registered at provincial level. | 0 Villages with land-use maps | 4 Villages have land-use maps for 450 households | 2.b Land-use maps and certificates. | 1. Shape files of land-use maps for 4 villages 2. Endorsement at Commune level | Annual | 1. Progress reports from the Department of Land Management, Urban Planning and Construction 2. Shape files 3. Land-use maps signed and stamped by Commune Chief | Livelihoods Project Officer
|  | 2.c Four villages endorse conservation agreements (3 1 by end of year 2, 4 by end of projectY3) | 0 Villages with conservation agreements | 4 Villages have conservation agreements that they respect | 2.c Village meeting minutes. | 1. Village level meetings to inform and ensure understanding of the Conservation Agreements 2. Signature of Conservation Agreements 3. Compliance review by Data Management Officer | Six-monthly | 1. Conservation agreements signed 2. Meeting minutes 3. Attendance list 4. Compliance database for rule breakers 5. Sales agreements from SMP; Trapeang digging contracts; vaccination contracts | Livelihoods Project Officer/SMP
Output 3 | Zoning plan of Western Siem Pang WS is developed in consultation with local communities | 3.a Zoning workplan is endorsed by the Zoning Working Group (provincial level representatives of the province and key departments) by end of Y2 | No zoning of WSPWS | Zoning Working Group is created and zoning workplan is endorsed | 3.a Zoning preparation plan and zonation process report | 1. Zoning Working Group is created and meetings are conducted 2. Zoning workplan is endorsed | Annual | 1. Official list of Zoning Working Group members 2. Zoning workplan 3. Meeting minutes 4. Attendance list 5. Zoning process review report | Livelihoods Programme Manager
|  | 3.b Draft of zoning plan is endorsed by seven Village Forums, the stakeholder forum, and the Zoning Working Group by end of Yr.3 | No zoning of WSPWS | Draft zoning plan is endorsed at Provincial level | 3.b List and signatures of Zoning Working Group members endorsing the draft zoning plan | 1. Zoning map is produced 2. Zoning map is endorsed at Provincial level | Annual | 1. Draft zoning map 2. Zoning map endorsed by Zoning Working Group 3. Meeting minutes | Livelihoods Programme Manager
Output 4 | Improved food security in four target villages (5,052 people) through improved local capacity in agriculture, increased income from wildlife-friendly rice sales, natural resource management and direct natural resource interventions. | 4.a 1000 beneficiaries (50% women) benefit from training in sustainable agriculture (300 in year 1, 400 in year 2, 300 in year 3). | 0 Beneficiaries receive training in sustainable agriculture | 1000 beneficiaries benefit from training in sustainable agriculture | 4.a-b Comparison of knowledge and attitudes of training beneficiaries through a participatory learning assessment undertaken at start and end of project. | 1. Meetings to inform and invite participants 2. Schedule of training sessions over a year 3. Pre-post test to test gain in knowledge | Six-monthly | 1. Meeting minutes 2. Attendance lists 3. Pre/post tests | Senior Community Officer/CRDT
|  | 4.b Local communities demonstrate greater knowledge and commitment to sustainable trapeang management | Local communities have no knowledge on Trapeang management | 10 selected Trapeangs are sustainably used by local communities from 4 villages | 4.a-b Comparison of knowledge and attitudes of training beneficiaries through a participatory learning assessment undertaken at start and end of project. | 1. Training provided on sustainable trapeang use 2. Participatory learning assessment | Annual | 1. Attendance lists 2. Pre/post tests 3. Participatory learning assessment | Senior Community Officer
|  | 4.c 300 households and 50% of buffalo benefit from vaccination and animal husbandry training scheme. | 0 Households benefit from vaccination | 300 households and 50% of buffalo benefit from vaccination and animal husbandry training scheme. | 4.c Vaccination report updates in Darwin reports Yr 1, 2 and 3. | 1. Schedule of vaccinations and husbandry training 2. Selection of voluntary participants 3. Report updates | Annual | 1. Attendance lists 2. Pre/post tests 3. Vaccinations report | Senior Community Officer
|  | 4.d 200 direct beneficiaries (40% female) from target villages close to the Trapeangs are actively engaged in sustainable land management through the digging of 10 waterholes (Trapeangs). Three Trapeangs are dug by the end of Y1 and seven by the end of Y2. | 0 Trapeangs are dug | 10 Trapeangs are dug | 4.d Employment agreements and receipts for work carried out digging Trapeangs. | 1. Labour workers are selected in the target villages 2. Contracts are signed 3. Follow-up on Trapeangs digging on site | Annual | 1. Employment agreements 2. Receipts for work carried out 3. Trapeangs map and pictures | Senior Community Officer
|  | 4.e The Participatory Rural Appraisal in 2018 shows that the perception of villagers is that fish stocks in dug Trapeangs has increased compared with Trapeangs that have not been dug. | Villagers perception is that fish stocks are low | Villagers perception is that fish stocks have increased | 4.e Question to villagers in Participatory Rural Appraisal 2018: Comparing Trapeangs that have been dug with Trapeangs that have not been dug, have fish stocks increased, stayed the same or decreased, or don’t know? | 1. Conduct Trapeangs monitoring report 2. Villagers' perception survey | Annual | 1. Trapeangs monitoring report 2. Villagers' perception survey | Biodiversity Senior Project Officer
|  | 4.f At least two villages certified as organic, wildlife-friendly rice producers | 0 Villages are organic or wildlife-friendly rice producers | 2 Villages certified as organic or wildlife-friendly rice producers | 4.f Organic and wildlife-friendly rice certificates. | 1. Participants follow the compliance criteria 2. Rice certificates are delivered after thorough evaluation | Annual | 1. Compliance database 2. Rice certificates | Livelihoods Project Officer/SMP
|  | 4.g 200 households (1000 people) involved in wildlife friendly rice production programme gain a minimum 10% income premium on rice sales. | 0 Households are involved in wildlife-friendly rice production | 200 Households are involved in wildlife-friendly rice production | 4.g Sale of rice receipts. | 1. Selection of voluntary households in 4 villages 2. Collection of rice receipts after the production is sold to SMP | Annual | 1. Households database 2. Rice receipts | Livelihoods Project Officer/SMP
Output 5 | Between 2018 and 2019 the area of forest converted to rice fields within the boundary of WSPWS has halved compared with the area converted between 2016 and 2017. | 5.b Ground truthed maps of rice fields produced in Y2 show only 5-10% encroachment took place between 2018 and 2019 and support data collected through landsat images | No maps of rice fields produced | Rice fields maps are produced and compliance analysis shows only 5-10% encroachment took place between 2018 and 2019 | 5.b Community ground truthed maps of rice fields. | 1. Department of Land Management helps produce the rice field maps within 4 villages 2. Compliance database compiles all changes for Y3 | Annual | 1. Shape file of rice field maps for 4 villages 2. Compliance database | Data Management Officer/SMP
|  | 5.a Landsat images show that the area of WSPWS converted to rice fields between 2018 and 2019 is half the area converted between 2016 and 2017. | Forest cover change report for 2016-2017 gives us the area converted to that date | Landsat images show that the area of WSPWS converted to rice fields between 2018 and 2019 is half the area converted between 2016 and 2017. | 5.a Landsat image analysis, final project report. | 1. Consultant produces analysis of the landsat images | Annual | 1. Forest cover change report | Data Management Officer
Output 6 | Increased awareness of the links between biodiversity and human-wellbeing and support for mainstreaming participatory forest management into sustainable protected forest management policy. | 6.a Comparison of workshop participatory learning results in Yr 1 and Yr 3 show target communities have greater awareness and commitment to sustainable forest management. | Local communities have limited awareness and commitment to sustainable forest management | In Yr 3, target communities have greater awareness and commitment to sustainable forest management. | 6.a Workshop minutes, project reports. | 1. Workshops conducted on Y1 and Y3 2. Report on target communities awareness | Annual | 1. Workshops minutes 2. Attendance lists 3. Report on target communities awareness | Livelihoods Programme Manager
|  | 6.b Provincial workshop minutes show questions and discussion following presentation on policy brief with policy brief shared to 40 national level Government representatives. | No provincial workshop conducted | Policy brief produced and attracts interest from national level Government representatives | 6.b.1 Workshop minutes, event photographs. 6.b.2 Policy brief document supplied to Darwin and Workshop minutes. | 1. Provincial workshop end of Y3 | Annual | 1. Workshop minutes 2. Pictures 3. Policy brief | Livelihoods Programme Manager
|  | 6.c Meeting minutes of BirdLife Asia meeting shows debate and evidences learning through questioning from regional partners. | No Birdlife Asia meeting conducted | Birdlife regional partners are interested in the achievements of the project and aim to use the lessons learned for their project sites | 6.c. Meeting minutes. | 1. Presentation at Birdlife Asia Meeting 2. Feedbacks from participants | Annual | 1. Presentation 2. Meeting minutes | Livelihoods Programme Manager
|  | 6.d Project case study shared on BirdLife International website/Facebook page attracts 2000 views | No case study shared | Case study produced and attracting 2000 views on Facebook and Birdlife website | 6.d Google analytics. | 1. Case studies production 2. Publication on internet platforms | Annual | 1. Case studies 2. Google analytics | Livelihoods Programme Manager
|  | 6.e Project case study shared on capacity for conservation website and accessed more than 100 times by conservation professionals | No case study shared | Case study attracts more than 100 views on capacity for conservation website | 6.e Capacity for conservation webpage access information available on website. | 1. Case studies production 2. Publication on Capacity for Conservation website | Annual | 1. Case studies 2. Google analytics | Livelihoods Programme Manager

## Reports-Surveys Deadlines
# | Report name | Output | Responsibility | Frequency | Deadline
1 | PRA Baselines | Outcome | Senior Community Officer | Yearly | Done
2 | Species census 2016 baseline | Outcome | Biodiversity Senior Project Officer | Yearly | Done
3 | PRA 2018 | Outcome | Senior Community Officer | Yearly | 31/01/2019
4 | Species census 2018 | Outcome | Biodiversity Senior Project Officer | Yearly | 31/01/2019
5 | Gender Representation Strategy | Output 1 | Livelihoods Programme Manager | Once | Done
6 | Participatory learning assessment survey | Output 1 | Livelihoods Project Officer | Quarterly | 31/12/2018
7 | Village level requests for zoning plan | Output 1 | Senior Community Officer | Once | Done
8 | Zoning process review report | Output 3 | Livelihoods Programme Manager | Once | 30/09/2018
9 | Participatory learning assessment for Trapeangs digging | Output 4 | Senior Community Officer | Six-monthly | 31/01/2019
10 | Vaccinations report | Output 4 | Senior Community Officer | Yearly | Done
11 | Trapeangs monitoring report | Output 4 | Biodiversity Senior Project Officer | Yearly | 31/01/2019
12 | Villagers' perception survey on fish stocks in Trapeangs | Output 4 | Senior Community Officer | Yearly | 31/01/2019
13 | Forest cover change report | Output 5 | Data Management Officer | Yearly | Done
14 | Target communities awareness report | Output 6 | Livelihoods Programme Manager | Once | 2019-03-01
15 | Policy Brief | Output 6 | Livelihoods Programme Manager | Once | Done